## README
3D Model Spec Sheet (Roblox, Blender pipeline)
Reusable template. One workbook per model. Built 2026-09-30 from STANDING-RULES 35b/38/40/45/47/51/55/57 + PIPELINE.md lessons.
How to use
1 | Fill the Brief tab first (subject, style, size, where it appears). Nothing downstream starts until the Brief is approved.
2 | List every mesh on the Parts tab with its triangle budget. Type the real triangle count after each Blender export; the sheet flags anything over budget or over Roblox's 20,000-per-mesh import cap.
3 | List every texture map on Textures; record asset IDs on Uploads after the Open Cloud upload (ClaudePlugins/tools/oc_upload.ps1).
4 | Work through the Acceptance tab. The model is DONE only when the Gate cell reads PASS (every required check = Pass or N/A).
Colour key
Yellow cell, blue text | Input: type here.
Light-blue row | Example row (a treasure chest) showing the expected format. Overwrite or delete it.
Black text, no fill | Formula: do not type over it.
Red / green fill | Automatic: over budget / failed check vs within budget / passed.
Hard limits (never overridden)
Money | NO money, NO Robux, credits or paid trials, ever. Free tools, free uploads and free accounts are all fine.
Access | Never make an experience public or change its access.
Crash safety | Never send non-image files to Studio upload_image/store_image. Material Maker is GUI only.
Roblox numbers used here
Tri cap per mesh | 20,000 triangles (Roblox import limit; split bigger hero props into several meshes sharing ONE atlas).
Texture size | 1024 px runtime maps are the default; up to 2048 only for a hero piece, and record why.
PBR | SurfaceAppearance: Color, Normal (OpenGL tangent space), Roughness, Metalness.

## Brief
Brief
One page. Approved once by the owner; then no back-and-forth (PIPELINE.md step 1).
Field | Value | Guidance
Model name | Treasure_Chest_Mythic | Short PascalCase; becomes the FBX / asset name.
Project / game | Inspect the Package | Which place it ships in, or 'standalone pack'.
Use | Game prop | Game prop / Pet / Character / Cosmetic / Environment / Sale pack
Art style | Cartoony Roblox-simulator: chunky bevels, candy colours, 1 shadow tone + 1 highlight | Match the game's art bible; no realistic render look unless asked.
Size in studs (L x W x H) | 4 x 2.6 x 3 | Measure against a 5-stud R15 avatar.
Where it appears | Hall of Fame shelf, reward popup preview, roam area | Rule 47: EVERY place it appears gets the same model.
Hero view distance (studs) | 8 | Closest normal camera distance; drives detail level.
Animated? | Lid open (hinge bone) | None / hinge / full rig (R15 or custom).
Premium / named item? | Yes: Mythic | Rule 30: premium gets VFX at Veilblade quality; plain items get none.
References (2-5) | refs/REF-01.png, refs/REF-02.png | Paths to the owner's reference images.
Front direction | -Z | Roblox front; previews sway, never spin (rule 36).
Resale planned? | No | If Yes: no Hunyuan3D-2 geometry, no Mixamo raw files, licences on Tools tab.
Owner approved on |  | Date the owner said the brief is final (rule 8).

## Parts
Parts and triangle budget
One row per exported mesh (MeshPart). Cap = 20,000 triangles per mesh.
Roblox tri cap per mesh |  | 20000
ID | Mesh name | What it is | LOD | Tri budget | Actual tris | % of budget | Budget check | Cap check | Material / atlas cell | Texture set | UVs 0-1, 1 set? | Status | Made with | Notes
P-01 | Chest_Body | Box, bevelled planks, metal corner caps | LOD0 | 9000 | 8420 | 93.56% | OK | OK | Atlas: Wood_A + Gold_Trim | TX-01 | Yes | Approved | Blender 5.2 | Corners are one mesh with the box (no floating caps).
P-02 | Chest_Lid |  | LOD0 | 6000
| TOTAL (LOD0 only) |  |  | 15000 | 8420 | 56.13% | 0 over | 0 to split
Note on C3: Roblox 3D Importer / Open Cloud mesh limit (PIPELINE.md, M2 lesson 2026-09-29).

## LODs
LOD plan
Targets vs actuals pulled from the Parts tab. Skip LOD1/2 for small props seen only up close.
LOD | Target total tris | Actual total tris (from Parts) | Check | Switch distance (studs) | Notes
LOD0 | 18000 | 8420 | OK | 0 | Hero; closest camera.
LOD1 | 8000 | 0 |  | 40 | Keep silhouette; merge small trims.
LOD2 | 2500 | 0 |  | 90 | Silhouette only.

## Textures
Texture maps
SurfaceAppearance set per atlas. Runtime default 1024 px; 2048 only for hero pieces (say why in Notes).
ID | Map name | Type | Resolution (px) | Size check | Atlas / used by | Made with | Asset ID | Notes
TX-01 | Chest_Color.png | Color | 1024 | OK | P-01, P-02 | Blender bake + Krita paint |  | Palette matches art bible; ~10% less saturated (rule 51).

## Acceptance
Acceptance gate
The model is done only when the Gate reads PASS. Every row comes from an owner rule or a past miss.
# | Area | Check | Source rule | Result | Evidence (screenshot / log path) | Notes
1 | Shape | Silhouette reads as the subject at a glance from 3 distances (hero, 25, 70 studs) | Lean-path 3 | Pending
2 | Shape | Matches the references side by side (proportions within ~3%) | PIPELINE 4 | Pending
3 | Shape | Made in Blender; no Studio primitive parts on anything visible | Rule 45 | Pending
4 | Shape | Any symbol or glyph on the model is one seamless mesh or a decal, never stacked parts | Rule 35b | Pending
5 | Clean geometry | No interpenetration, z-fighting, floating gaps or parts poking through (automated overlap audit + close-ups) | Lean-path 6 / Rule 47 | Pending
6 | Clean geometry | Resting contact: sits ON its surface, no float, no sinking | Rule 51 | Pending
7 | Clean geometry | Raycast support audit: 4 bottom corners + centre, float <= 0.03 studs, no unsupported corner (legs/feet/stands included) | Rule 55 | Pending
8 | Clean geometry | Nothing lies over or through a functional surface (belts, walk paths, desk work area, seats) | Rule 57 | Pending
9 | Clean geometry | Normals outward, no non-manifold edges, no zero-area faces; FBX re-import shows 0 problems | PIPELINE M1/M2 | Pending
10 | Mesh and UV | Every mesh <= 20,000 tris (Parts tab shows 0 to split) | Roblox cap | Pending
11 | Mesh and UV | Several sizes of one family = one mesh per size, not non-uniform scaling | PIPELINE M2 | Pending
12 | Mesh and UV | One 0-1 UV set per mesh; shared atlas across split parts | PIPELINE M2 | Pending
13 | Look | Colour matches the name and no lookalike with another item (contact sheet) | Rule 40 | Pending
14 | Look | Colour grade ~10% less saturated than first instinct; bright and toy-like, not blown out | Rule 51 / 42 | Pending
15 | Look | Premium item: effects at Veilblade quality in the game's style; plain item: no effects | Rule 30 | Pending
16 | Look | Shines and glints stay on the surface, never stick out into the air | Rule 38 | Pending
17 | Views | Close-ups from several angles INCLUDING low back corners, not just hero shots | Rule 51 / 55 | Pending
18 | Views | 3D previews keep the front toward the viewer (sway, not spin) | Rule 36 | Pending
19 | Views | Swapped in at EVERY place it appears (shelves, previews, cards, tutorial) | Rule 47 | Pending
20 | Pipeline | Pivot / PrimaryPart PivotOffset set to the intended origin; front = -Z | PIPELINE P2 | Pending
21 | Pipeline | Uploaded via Open Cloud; asset IDs written into source (no Studio-only edits) | Rule 39 | Pending
22 | Pipeline | Old stand-in or placeholder removed WITH its code | Rule 53 | Pending
23 | Pipeline | Licences recorded; no Hunyuan3D-2 geometry if resale planned | Tools tab | Pending
24 | Budget | Zero money / Robux spent | Hard limit | Pending
|  | Passed | 0
|  | N/A | 0
|  | Failed | 0
|  | Pending | 24
|  | Total checks | 24
|  | GATE | NOT YET

## Uploads
Uploads and wiring
Every uploaded file. Tool: ClaudePlugins/tools/oc_upload.ps1 (key read from env, never printed).
File | Kind | Asset ID | Creator | Uploaded (date) | Wired into (source path) | In place (verified)? | Notes
Chest_Mythic.fbx | Mesh |  | User 513451560 |  | SRC/shared/Assets.luau | No | Group experiences need asset-use permission granted.

## Tools
Toolchain and licences
All free. Re-verify licences each project (lean-path 1). Nothing here costs money.
Step | Tool | Cost | Commercial use in games | Resale of the asset | Catch
Concept frames | ComfyUI + FLUX.1-schnell / SDXL / Qwen-Image (local, D:\AI) | $0 | Yes | Yes | Style frames only; not shipped.
Base shape (optional) | Hunyuan3D-2 (local) | $0 | Yes (not EU/UK/KR) | No | Shape guide only; never shipped geometry in sale packs.
Modeling / retopo / UV / bake | Blender 5.2 + Roblox add-on | $0 | Yes | Yes | Your output is yours (GPL covers the program, not your models).
Anime characters | VRoid Studio + Blender VRM add-on | $0 | Yes | Yes | Scripted faces not acceptable for anime (lean-path 1).
Rig / animation base | Mixamo (owner's Adobe login) + Blender retarget | $0 | Yes, inside games | No (raw files) | Hand-polish hero moves.
PBR textures | Material Maker (GUI only) / Blender / Krita | $0 | Yes | Yes | Material Maker CLI crashes: GUI only.
Upscale / cutout | Real-ESRGAN, rembg | $0 | Yes | Yes
Upload | Open Cloud via oc_upload.ps1 | $0 | Yes | n/a | Key in USER env var ROBLOX_API_KEY; never printed or logged.